## Proj Timeline w Milestone
VIRTUAL EYE - LIFEGUARD FOR SWIMMING POOLS TO DETECT ACTIVE DROWNING - MILESTONE AND ACTIVITY LIST (TEAM ID - PNT2022TMID23045)
|  | AUGUST | [7 empty] | SEPTEMBER | [25 empty] | OCTOBER | [25 empty] | NOVEMBER
|  | 22 | 23 | 24 | 25 | 26 | 27 | 29 | 30 | 1 | 2 | 3 | 5 | 6 | 7 | 8 | 9 | 10 | 12 | 13 | 14 | 15 | 16 | 17 | 19 | 20 | 21 | 22 | 23 | 24 | 26 | 27 | 28 | 29 | 30 | 1 | 3 | 4 | 5 | 6 | 7 | 8 | 10 | 11 | 12 | 13 | 14 | 15 | 17 | 18 | 19 | 20 | 21 | 22 | 24 | 25 | 26 | 27 | 28 | 29 | 31 | 1 | 2 | 3 | 4 | 5 | 7 | 8 | 9 | 10 | 11 | 12 | 14 | 15 | 16 | 17 | 18 | 19
|  | WEEK - 1 | [5 empty] | WEEK - 2 |  |  |  |  | WEEK - 3 | [5 empty] | WEEK - 4 | [5 empty] | WEEK - 5 | [5 empty] | WEEK - 6 | [5 empty] | WEEK - 7 | [5 empty] | WEEK - 8 | [5 empty] | WEEK - 9 | [5 empty] | WEEK - 10 | [5 empty] | WEEK - 11 | [5 empty] | WEEK - 12 | [5 empty] | WEEK - 13
ACTIVITY I
Project Objectives
ACTIVITY II
Prior Knowledge
ACTIVITY III
Prerequisites
ACTIVITY IV
Project Structure
ACTIVITY V
Cloudant DB
ACTIVITY VI
Application Building | bar: AUGUST 29 to SEPTEMBER 3
ACTIVITY VII
Ideation phase | bar: AUGUST 29 to SEPTEMBER 3
ACTIVITY VIII
Project Design Phase – I | bar: SEPTEMBER 19 to SEPTEMBER 22
ACTIVITY IX
Project Design Phase – II | bar: OCTOBER 5 to OCTOBER 8
ACTIVITY X
Project Planning Phase | bar: OCTOBER 22
ACTIVITY XI
Project Development Phase | bar: OCTOBER 24 to OCTOBER 27
PROJECT END
Install python packages
Register & Login to IBM Cloud
Create Service Instance
Creating service credentials
Launch Cloudant DB
Create Database
Build Python Code
Run the Application
Output
Build HTML pages
Literature survey on the selected project & Information Gathering
Prepare Empathy Map
Ideation
Proposed Solution
Problem Solution Fit
Solution Architecture
Customer Journey
Functional Requirement
Data Flow Diagrams
Technology Architecture
Prepare Milestone & Activity List
Sprint Delivery Plan
Project Development - Delivery of Sprint-1
Project Development - Delivery of Sprint-2
Project Development - Delivery of Sprint-3
Project Development - Delivery of Sprint-4